## Instructions
Project Plan Instructions
The project plan is meant to capture key project milestones intended to be met during the lifetime of the project. Details of the project plan will be dependent upon the scope associated with the project and may look differently if funded for the development of a plan versus construction. A project plan should be completed for each year of funding awarded. Not all projects will have a full 12 month implementation period, so please be sure to align your project plan with the funding timeline associated with your award. An example project plan is provided in the purple tab. Please review the example project plan before developing your own to ensure that your project plan is completed with all required details.The project plan template in the green tab is for planning purposes only. You will enter your project plan directly into your application via Salesforce.
Project Milestones: | Project milestones should be considered as key tasks needed to occur to see the project through to completion.
Task Assigned to: | Should include the person(s) responsible for seeing the milestone through to completion. Tasks may be assigned to the applicant agency staff and/or subcontractors that are hired to do the work.
Begin by: | Begin by date should be the date by which work on the milestone should begin
End by: | End by date should be the date by which the milestone should be met.
Actual Start Date: | Start date by which the task actually began.
Actual End Date: | End date by which the task actually ended.
Task Status: | Click on the cell to reveal a drop down menu with three options (Not Started, In Progress, Complete)
Notes: | Enter any relevant notes to the associated milestone. Notes may include steps still needed, any challenges, successes, questions, etc. Should there be any potential risks or issues encountered, please document those in the notes section for the appropriate milestone(s).

## Project Plan
Year 1
Project Milestones | Task Assigned to | Begin by | End by | Actual Start Date | Actual End Date | Task Status | Notes
Preconstruction Tasks: Design Scope, Estimates, Relocation of Utilities, Permits | Contractors, OMRF Facilities, TIHO Leadership | 2025-12-08 | 2026-08-18 | 2025-12-08 | 2026-08-18 | Complete | Site evaluation, surveying, civil engineering assessments, design development, supplier/contractor selection, and permitting for the Advanced Human Imaging Center already underway and will be completed by 12/31/2025.
TIHO/AHIF Demo and Site Utility Construction | Contractors | 2026-06-01 | 2026-07-31 | 2026-08-03 | 2026-09-30 | Complete | Supported by TSET funding for construction
TIHO/AHIF Earthwork and Foundation | Contractors | 2026-09-17 | 2026-11-04 | 2026-09-17 | n/a | In Progress | Supported by TSET funding for construction
TIHO/AHIF Steel Structure Erection & Elevated Slabs | Contractors | 2026-11-05 | 2026-12-30 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO - assemble internal and external advisory committees | TIHO Leadership Faculty | 2026-01-01 | 2026-03-31 | 2026-01-01 | 2026-06-30 | Complete
TIHO - OMRF staff duties assignments | TIHO Leadership Faculty | 2026-04-01 | 2026-06-30 | 2026-04-01 | 2026-06-30 | Complete | Supported by TSET funding for staffing including TIHO project manager, TSET Biorepository Hub Manager/Technician, CRI Hub Database Manager, CRI Hub Data Librarian/Data Analyst, and HPH: Project Manager. Funds will also be used to purchase an annual subscription for the NIH Toolbox that will be used to administer various standardized cognitive tests as well as computing storage and infrastructure.
Telehealth and Distributed Trial Hub - search for and secure coordinator | TIHO Leadership Faculty | 2026-06-01 | 2026-09-30 | 2026-06-01 | 2026-09-30 | Complete | TSET funding support for TDT Coordinator
Telehealth and Distributed Trial Hub - meet with consultants to develop and implement tools for distant monitoring | TSET Hubs staff | 2026-10-01 | 2026-12-31 | 2026-10-01 | n/a | In Progress | Supported by TSET funding Telehealth consultant costs to develop and implement tools for distant monitoring, such as thermograms, cardiac monitoring, etc. The OCTSI/OSCTR has built an Evaluation Core which provides external Evaluation for OCTSI/OSCTR Programs and has also done multiple evaluation programs for tribal facilities, the Tribal Epidemiology Unit, and other organizations. Dr. Janis Campbell is an Associate Professor at the adjacent OUHSC and she and her unit will be hired to perform evaluation services for the TIHO. The approximate $6.4M requested will finish out the 2nd and 3rd floors of the Advanced Human Imaging Center for which over $7.45M is already raised as matching funds. These renovations include all architectural and design services, site prep, contractor activitities, plumbing, electrical, technology, furniture, fixtures and equipment. Detailed bids and cost estimates are available as needed.
Biorepository Hub - establish TIHO biorepository, transition samples into the TIHO biorepository, develop sample sharing processes/policies | TSET Biorepository staff | 2026-01-01 | 2026-12-31 | 2026-01-01 | n/a | In Progress
Human Performance Hub - develop educational content | TSET Human Performance Hub staff | 2026-07-01 | 2026-12-31 | 2026-10-01 | n/a | In Progress
Year 2
Project Milestones | Task Assigned to | Begin by | End by | Actual Start Date | Actual End Date | Task Status | Notes
TIHO/AHIF Exterior Framing, Sheathing, and Waterproofing | Contractors | 2027-01-01 | 2027-02-03 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF Roofing | Contractors | 2027-01-28 | 2027-02-10 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF MEP Rough | Contractors | 2027-01-28 | 2027-04-07 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF Interior Framing - Majority of Building Complete | Contractors | 2027-02-18 | 2027-03-31 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF In-wall Rough-In | Contractors | 2027-03-18 | 2027-03-05 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF Exterior Veneers | Contractors | 2027-02-04 | 2027-04-28 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF Curtainwall and Windows | Contractors | 2027-02-04 | 2027-03-17 | n/a | n/a | Not Started | Supported by TSET funding for construction
TIHO/AHIF Sheetrock, Tape, Bed, Paint | Contractors | 2027-04-29 | 2027-06-09 | n/a | n/a | Not Started | Supported by TSET funding for finishes
TIHO/AHIF Ceilings | Contractors | 2027-06-10 | 2027-06-30 | n/a | n/a | Not Started | Supported by TSET funding for finishes
TIHO/AHIF Millwork and Flooring | Contractors | 2027-07-01 | 2027-07-21 | n/a | n/a | Not Started | Supported by TSET funding for finishes
TIHO/AHIF Final Paint and Punchlist | Contractors | 2027-07-22 | 2027-08-11 | n/a | n/a | Not Started | Supported by TSET funding for finishes
TIHO/AHIF Sitework and Canopies | Contractors | 2027-04-29 | 2027-06-09 | n/a | n/a | Not Started | Supported by TSET funding for finishes
TIHO/AHIF - Install equipment, signage and FFE (Furniture, Fixtures, and Equipment) | Contractors | 2027-03-12 | 2027-04-29 | n/a | n/a | Not Started | TSET funds will be used to support the installation of equipment to the 2nd and 3rd floors, including Computing connection it I2, computing cabelling, high performance computing nodes and storage for CRI/TDT, ECG and Benchtop centrifuge (Eppendorf Centrifuge 5810R) for HPH, and clinical Exam Room Equipment (exam table, patient chairs, physician stool, EMR work station) for the CRI. Funding will also be used to install TSET and Tobacco-Free signage.
TIHO/AHIF - Commissioning and Punch | Contractors | 2027-08-12 | 2027-09-01 | n/a | n/a | Not Started | Supported by TSET funding
TIHO/AHIF - Final Inspections | Contractors | 2027-09-02 | 2027-09-22 | n/a | n/a | Not Started | Supported by TSET funding for final inspections
TIHO/AHIF - Certificate of Occupancy | TIHO Leadership Faculty | 2027-09-02 | 2027-09-22 | n/a | n/a | Not Started | Supported by TSET funding for certificate of occupancy
TIHO/AHIF - Grand Opening Ribbon Cutting Ceremony | TIHO Leadership Faculty, TSET Hubs Staff, TSET Leadership, OMRF Leadership, Community Leaders | 2027-09-22 | 2027-09-22 | n/a | n/a | Not Started | Partial TSET funding support for ribbon cutting ceremony
TIHO Human Performance Hub - renovations | Contractors | 2027-08-01 | 2028-04-30 | n/a | n/a | Not Started | Supported by TSET funding for renovation of Ground Floor in the OMRF Tower
Clinical Research and Informatics Hub - search for and secure medical director | TIHO Leadership Faculty | 2027-01-01 | 2027-03-31 | n/a | n/a | Not Started | Partial TSET funding support for CRI Director
Establish healthspan and healthy aging cohort | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | To include partial TSET funding support for HPH Director and Project Manager
Recruit and onboard telehealth and mobile outreach sites | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | TSET funding will be used to support rural practice telehealth and clinical research training workshops
Implement participant testing | TEST Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started
Establish and launch community engagement and outreach plan | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | TSET funding will be used to support patient education programs
Establish participant database | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started
Year 3
Project Milestones | Task Assigned to | Begin by | End by | Actual Start Date | Actual End Date | Task Status | Notes
Build healthy aging cohort | TSET Hubs staff | 2028-01-01 | 2028-12-31 | n/a | n/a | Not Started
Conduct clinical trials | TSET Hubs staff | 2028-01-01 | 2028-12-31 | n/a | n/a | Not Started
Continue community engagement and mobile outreach | TSET Hubs staff | 2028-01-01 | 2028-12-31 | n/a | n/a | Not Started | TSET funding support for TDT Coordinator OCTSI Community Engagement Services (OPHIC), rural practice telehealth and clinical research training workshops and support patient education programs
Conduct patient education | TSET Hubs staff | 2027-01-01 | 2028-12-31 | n/a | n/a | Not Started
Note on A2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommend noting exactly which milestones that TSET would be funding and aligning with the budget
Note on G2: Click cell for drop down menu
Note on G14: Click cell for drop down menu
Note on A31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recommend incorporating a milestone for TSET and tobacco free signage installation Reply: Added signage installation to row 22 but can move elsewhere as needed.
Note on G40: Click cell for drop down menu

## Dashboard_Data
Year | Project_Type | Project Milestones | Task Assigned to | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Task Status | Notes
2026 - Year 1 | Construction | Preconstruction Tasks: Design Scope, Estimates, Relocation of Utilities, Permits | Contractors, OMRF Facilities, TIHO Leadership | 2025-12-08 | 2026-08-18 | 2025-12-08 | 2026-08-18 | Complete | Site evaluation, surveying, civil engineering assessments, design development, supplier/contractor selection, and permitting for the Advanced Human Imaging Center already underway and will be completed by 12/31/2025.
2026 - Year 1 | Construction | TIHO/AHIF Demo and Site Utility Construction | Contractors | 2026-06-01 | 2026-07-31 | 2026-08-03 | 2026-09-30 | Complete | Supported by TSET funding for construction
2026 - Year 1 | Construction | TIHO/AHIF Earthwork and Foundation | Contractors | 2026-09-17 | 2026-11-04 | 2026-09-17 | n/a | In Progress | Supported by TSET funding for construction
2026 - Year 1 | Construction | TIHO/AHIF Steel Structure Erection & Elevated Slabs | Contractors | 2026-11-05 | 2026-12-30 | n/a | n/a | Not Started | Supported by TSET funding for construction
2026 - Year 1 | Administrative | TIHO - assemble internal and external advisory committees | TIHO Leadership Faculty | 2026-01-01 | 2026-03-31 | 2026-01-01 | 2026-06-30 | Complete | 0
2026 - Year 1 | Administrative | TIHO - OMRF staff duties assignments | TIHO Leadership Faculty | 2026-04-01 | 2026-06-30 | 2026-04-01 | 2026-06-30 | Complete | Supported by TSET funding for staffing including TIHO project manager, TSET Biorepository Hub Manager/Technician, CRI Hub Database Manager, CRI Hub Data Librarian/Data Analyst, and HPH: Project Manager. Funds will also be used to purchase an annual subscription for the NIH Toolbox that will be used to administer various standardized cognitive tests as well as computing storage and infrastructure.
2026 - Year 1 | Administrative | Telehealth and Distributed Trial Hub - search for and secure coordinator | TIHO Leadership Faculty | 2026-06-01 | 2026-09-30 | 2026-06-01 | 2026-09-30 | Complete | TSET funding support for TDT Coordinator
2026 - Year 1 | Administrative | Telehealth and Distributed Trial Hub - meet with consultants to develop and implement tools for distant monitoring | TSET Hubs staff | 2026-10-01 | 2026-12-31 | 2026-10-01 | n/a | In Progress | Supported by TSET funding Telehealth consultant costs to develop and implement tools for distant monitoring, such as thermograms, cardiac monitoring, etc. The OCTSI/OSCTR has built an Evaluation Core which provides external Evaluation for OCTSI/OSCTR Programs and has also done multiple evaluation programs for tribal facilities, the Tribal Epidemiology Unit, and other organizations. Dr. Janis Campbell is an Associate Professor at the adjacent OUHSC and she and her unit will be hired to perform evaluation services for the TIHO. The approximate $6.4M requested will finish out the 2nd and 3rd floors of the Advanced Human Imaging Center for which over $7.45M is already raised as matching funds. These renovations include all architectural and design services, site prep, contractor activitities, plumbing, electrical, technology, furniture, fixtures and equipment. Detailed bids and cost estimates are available as needed.
2026 - Year 1 | Administrative | Biorepository Hub - establish TIHO biorepository, transition samples into the TIHO biorepository, develop sample sharing processes/policies | TSET Biorepository staff | 2026-01-01 | 2026-12-31 | 2026-01-01 | n/a | In Progress | 0
2026 - Year 1 | Administrative | Human Performance Hub - develop educational content | TSET Human Performance Hub staff | 2026-07-01 | 2026-12-31 | 2026-10-01 | n/a | In Progress | 0
2027 - Year 2 | Construction | TIHO/AHIF Exterior Framing, Sheathing, and Waterproofing | Contractors | 2027-01-01 | 2027-02-03 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF Roofing | Contractors | 2027-01-28 | 2027-02-10 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF MEP Rough | Contractors | 2027-01-28 | 2027-04-07 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF Interior Framing - Majority of Building Complete | Contractors | 2027-02-18 | 2027-03-31 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF In-wall Rough-In | Contractors | 2027-03-18 | 2027-03-05 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF Exterior Veneers | Contractors | 2027-02-04 | 2027-04-28 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF Curtainwall and Windows | Contractors | 2027-02-04 | 2027-03-17 | n/a | n/a | Not Started | Supported by TSET funding for construction
2027 - Year 2 | Construction | TIHO/AHIF Sheetrock, Tape, Bed, Paint | Contractors | 2027-04-29 | 2027-06-09 | n/a | n/a | Not Started | Supported by TSET funding for finishes
2027 - Year 2 | Construction | TIHO/AHIF Ceilings | Contractors | 2027-06-10 | 2027-06-30 | n/a | n/a | Not Started | Supported by TSET funding for finishes
2027 - Year 2 | Construction | TIHO/AHIF Millwork and Flooring | Contractors | 2027-07-01 | 2027-07-21 | n/a | n/a | Not Started | Supported by TSET funding for finishes
2027 - Year 2 | Construction | TIHO/AHIF Final Paint and Punchlist | Contractors | 2027-07-22 | 2027-08-11 | n/a | n/a | Not Started | Supported by TSET funding for finishes
2027 - Year 2 | Construction | TIHO/AHIF Sitework and Canopies | Contractors | 2027-04-29 | 2027-06-09 | n/a | n/a | Not Started | Supported by TSET funding for finishes
2027 - Year 2 | Construction | TIHO/AHIF - Install equipment, signage and FFE (Furniture, Fixtures, and Equipment) | Contractors | 2027-03-12 | 2027-04-29 | n/a | n/a | Not Started | TSET funds will be used to support the installation of equipment to the 2nd and 3rd floors, including Computing connection it I2, computing cabelling, high performance computing nodes and storage for CRI/TDT, ECG and Benchtop centrifuge (Eppendorf Centrifuge 5810R) for HPH, and clinical Exam Room Equipment (exam table, patient chairs, physician stool, EMR work station) for the CRI. Funding will also be used to install TSET and Tobacco-Free signage.
2027 - Year 2 | Construction | TIHO/AHIF - Commissioning and Punch | Contractors | 2027-08-12 | 2027-09-01 | n/a | n/a | Not Started | Supported by TSET funding
2027 - Year 2 | Construction | TIHO/AHIF - Final Inspections | Contractors | 2027-09-02 | 2027-09-22 | n/a | n/a | Not Started | Supported by TSET funding for final inspections
2027 - Year 2 | Construction | TIHO/AHIF - Certificate of Occupancy | TIHO Leadership Faculty | 2027-09-02 | 2027-09-22 | n/a | n/a | Not Started | Supported by TSET funding for certificate of occupancy
2027 - Year 2 | Construction | TIHO/AHIF - Grand Opening Ribbon Cutting Ceremony | TIHO Leadership Faculty, TSET Hubs Staff, TSET Leadership, OMRF Leadership, Community Leaders | 2027-09-22 | 2027-09-22 | n/a | n/a | Not Started | Partial TSET funding support for ribbon cutting ceremony
2027 - Year 2 | Construction | TIHO Human Performance Hub - renovations | Contractors | 2027-08-01 | 2028-04-30 | n/a | n/a | Not Started | Supported by TSET funding for renovation of Ground Floor in the OMRF Tower
2027 - Year 2 | Administrative | Clinical Research and Informatics Hub - search for and secure medical director | TIHO Leadership Faculty | 2027-01-01 | 2027-03-31 | n/a | n/a | Not Started | Partial TSET funding support for CRI Director
2027 - Year 2 | Administrative | Establish healthspan and healthy aging cohort | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | To include partial TSET funding support for HPH Director and Project Manager
2027 - Year 2 | Administrative | Recruit and onboard telehealth and mobile outreach sites | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | TSET funding will be used to support rural practice telehealth and clinical research training workshops
2027 - Year 2 | Administrative | Implement participant testing | TEST Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | 0
2027 - Year 2 | Administrative | Establish and launch community engagement and outreach plan | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | TSET funding will be used to support patient education programs
2027 - Year 2 | Administrative | Establish participant database | TSET Hubs staff | 2027-01-01 | 2027-12-31 | n/a | n/a | Not Started | 0
2028 - Year 3 | Administrative | Build healthy aging cohort | TSET Hubs staff | 2028-01-01 | 2028-12-31 | n/a | n/a | Not Started | 0
2028 - Year 3 | Administrative | Conduct clinical trials | TSET Hubs staff | 2028-01-01 | 2028-12-31 | n/a | n/a | Not Started | 0
2028 - Year 3 | Administrative | Continue community engagement and mobile outreach | TSET Hubs staff | 2028-01-01 | 2028-12-31 | n/a | n/a | Not Started | TSET funding support for TDT Coordinator OCTSI Community Engagement Services (OPHIC), rural practice telehealth and clinical research training workshops and support patient education programs
2028 - Year 3 | Administrative | Conduct patient education | TSET Hubs staff | 2027-01-01 | 2028-12-31 | n/a | n/a | Not Started | 0